## Epic Stories
SPIDERBRO Backlog |  | Milestone 2 |  | Members | Name | Alias
[5 empty] | Dallen | DF
[5 empty] | Greg | GH
[5 empty] | Nigel | NN
[5 empty] | Doug | DV
Status | Title [Estimation time in hrs] | Description | Time Taken (hrs) | Completion Date | Members | Labels | Card # | Card URL
Done | Submittables / Grading [1] |  | 1 |  |  | M2 Requirement | 8 | https://trello.com/c/6ocZmdmE
Done | Individual Progress Reports | Each member of the group should turn in a separate progress report. Submit a plain text/html file including: * A rating of each of the other members of your group. * how much they contributed to the project * how well they communicated with the group. * The rating should be on a scale of 1 to 5, with 5 being the best. You can also include comments. |  | 2015-10-15 16:00 |  | M2 Requirement | 6 | https://trello.com/c/FpWgZWYy
Done | Game design document [3] | Write a game design document that describes the design and implementation of your group's game * Start from Pitch * include information about the software design * implementation of the game, Collab Doc Here: https://docs.google.com/document/d/1vkhe1z7SB_qGJzgdHhzdKpMxdQyyBWziZdrJczPwTfs | 3 | 2015-10-15 16:00 | DF,GH,DV,NN | M2 Requirement | 2 | https://trello.com/c/EjCdEH7u
Done | Use of Backlog | As group members complete implementation of user stories in the backlog, add information to your group's backlog.xls (trello, we will export this information to excel) Each Story should have: * Completion date * Assignee * Time logged |  | 2015-10-15 16:00 | DV,DF,GH,NN | M2 Requirement | 3 | https://trello.com/c/UWEzv6Ps
Done | Add variable "R" to restart game modifiable [0.5] |  | 0.5 | 2015-10-13 12:00 | NN,DV,DF |  | 38 | https://trello.com/c/GyxhOARL
Done | Game over UI [1] |  | 1 | 2015-10-13 12:00 | NN,DV |  | 26 | https://trello.com/c/Ty97U7zN
Done | Plan for Milestone 3 [0.5] | * Explain which user stories you will be implementing for Milestone 3 * Explain how they relate to the feedback you receive and the game design concepts we talk about in class. | 0.5 |  | DV,DF,GH | M2 Requirement | 4 | https://trello.com/c/2r5Jegu6
Done | Enemy Basic AI [5] | Enemies will spawn and then ignore the player entirely and then make a straight bee-line toward the mouth/center of level. | 5 | 2015-10-13 12:00 | NN,GH | M2 Requirement | 13 | https://trello.com/c/tW1G6IuY
Done | Spawner and Level Re-Do [5] | Greg's spawner gets implemented with a slightly bigger/better level design. Suggest adding the bed from this page: https://www.assetstore.unity3d.com/en/#!/content/8329 (free unity asset store) | 5 | 2015-10-15 16:00 | GH,DF | M2 Requirement | 35 | https://trello.com/c/ZO3YxZdI
Done | Update ReadMe [0.5] | README.html or README.txt file that includes the following sections: * how to play your game, * your group's plan for Milestone 3, * repository information. | 0.5 |  | DV,DF | M2 Requirement | 7 | https://trello.com/c/9TS0ggTC
Done | Character Attack 2 (spit) [3] | Attack2 implementation: fires a single projectile in a parabolic arc. If the projectile object hits an enemy object’s hitbox, it does a small amount of hp damage, and apply a slow effect that will slow that enemies movement rate for 10 seconds. Player can aim mouse higher to increase the arc of the fired projectile, etc. Player starts with three shots, and needs to wait 25 seconds (subject to change), before a shot will ‘recharge’ and be able to be shot again. | 3 | 2015-10-12 12:00 | NN,DV | M2 Requirement | 12 | https://trello.com/c/ackeaFUj
Done | Get Basic game from M1 to Repo [2] |  | 1 | 2015-10-02 12:00 | DV |  | 30 | https://trello.com/c/YKi42Jzw
Done | Beginning UI (Start Game) |  | 1.5 | 2015-10-14 12:00 | NN |  | 24 | https://trello.com/c/3HR9V7Vf
Done | UI : Spit Ammo HUD |  | 1.5 | 2015-10-14 12:00 | NN |  | 33 | https://trello.com/c/bQXJI8BG
Done | Repository Information [0.5] | Update Readme.txt to include: * Where the GitHub repository is located * How the professor can access it | 0.5 | 2015-10-14 12:00 | DV | M2 Requirement | 5 | https://trello.com/c/zujDAx9j
Done | UI : Timer [0.5] |  | 0.5 | 2015-10-13 12:00 | NN |  | 18 | https://trello.com/c/hs8bjeXT
Done | UI : Health [0.5] |  | 0.5 | 2015-10-13 12:00 | NN |  | 19 | https://trello.com/c/bPVwwY9X
Done | Character Attack 1 (bite) [3] | Attack1 implementation: triggers a bite animation from player object and uses a collision box that extends slightly from the spiders mouth. If an enemy is touching or in that box, when mouse1 is pressed, that enemy will take hp damage. | 3 | 2015-10-13 12:00 | DF | M2 Requirement | 31 | https://trello.com/c/jbCLyCqw
Done | Game is Playable [5] | Game should include all of the most important features in the game, even if they are somewhat simplified. The idea is to get other people to play your game and give you feedback. If your game doesn't give players a good feel for what the game is about, they probably won't be able to provide useful feedback. | 8 | 2015-10-14 12:00 | DV,DF,GH,NN | M2 Requirement | 1 | https://trello.com/c/LGfNo3Qh
Done | Character Movement [0.5] |  | 0.5 | 2015-10-13 12:00 | DF | M2 Requirement | 9 | https://trello.com/c/sS6FA3Qu
Done | Research scene collaboration [0.5] |  | 0.5 | 2015-10-15 16:00 | NN |  | 34 | https://trello.com/c/2U8BVSlY
Done | Level Model [1] |  | 1 | 2015-10-13 12:00 | GH |  | 22 | https://trello.com/c/d57loNfv
Done | Game over Logic [1] |  | 1 | 2015-10-13 12:00 | NN,DV,DF |  | 27 | https://trello.com/c/hayfcbT6
Backlog | Character Model |  |  |  |  | M3 Requirement,M2 Requirement | 10 | https://trello.com/c/a1VWNXXx
Backlog | Character Camera | 1st Person camera as spider, and 3rd person camera as spider. |  |  |  | M2 Requirement,M3 Requirement | 11 | https://trello.com/c/eCpZoP33
Backlog | Character Attack 3 (web trap) | Attack3 implementation: player leaves a web trap object on the floor. If an enemy runs into the web trap's collision box, it will trigger and the enemy will be rendered immobile for 20 seconds (subject to change). The enemy is then freed and the web trap object deletes itself. The player may only place a limited number of these and needs to either wait a certain time for it to regen or kill a certain enemy to regen. |  |  |  | M3 Requirement | 32 | https://trello.com/c/4WWIBcx2
Backlog | Enemy Intermediate AI | Enemies will find the shortest path toward mouth using a waypoint system. Each node in the waypoint system will be an invisible object. Uses shortest path algorithm to find best path. If player is encountered while enroute, it will leave path and attack player. If player disappears form line of view, will return to closest node and then recalculate shortest path. |  |  |  | M3 Requirement | 14 | https://trello.com/c/pKKQ0u6m
Backlog | Enemy Advanced AI | Enemy units have a personality script that does a couple of things. When first spawned randomly decides how: aggressive, wandering, hard. Aggressive == how likely is it to follow the player. Wandering == how likely is it to wander around the map or go toward mouth. Hard == How many attacks does it make per second. 0% == no chance 100% == Always happens/Best Efficiency This is added on top of our basic intermediate AI. |  |  |  | M4 Requirement | 15 | https://trello.com/c/AxbkOO6Z
Backlog | Enemy Die [2] | replace existing die method. * splat for projectile * opacity slider.... for enemy | 2 |  | DV |  | 17 | https://trello.com/c/nrStduSl
Backlog | Enemy Attack |  |  |  |  | M3 Requirement | 16 | https://trello.com/c/mIN89Neq
Backlog | UI : Current Weapon | [5 empty] | 20 | https://trello.com/c/xsAqP4DZ
Backlog | UI : Wave Count | [5 empty] | 21 | https://trello.com/c/KaKBoFHF
Backlog | Level Objects | [5 empty] | 23 | https://trello.com/c/Io0TfoFD
Backlog | Pause UI | [5 empty] | 25 | https://trello.com/c/Qne1WBwe
Backlog | NPC and Player Stats | NPCs will have 30-75hp, and attack1 does 25dmg, attack2 does 10dmg. These stats will track current hp. Attack2 also slows down it's target for 10 seconds. NPCs will also give player +25 xp for killing them. There are three types of xp: coachroachXP, earwigXP, somethingelseXP - as each stat increases, your dmg for each attack increases. |  |  | DV,DF | M3 Requirement | 36 | https://trello.com/c/wbCplRwA
Backlog | Completed Level | This is the completed bedroom level. Has all the fancy details. Steps: 1. Draw a map outline 2. Start implementing map outline using existing terrain and models 3. Add details to map eg: additional models, lighting, and effects 4. Build spawner in mind with this map. |  |  | GH,DF | M3 Requirement,M4 Requirement | 37 | https://trello.com/c/LYU27GZq

## Archived Epic Stories
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL