## Epic Stories
SPIDERBRO Backlog |  | Milestone 4 |  | Members | Name | Alias
[5 empty] | Dallen | DF
[5 empty] | Greg | GH
[5 empty] | Nigel | NN
[5 empty] | Doug | DV
Status | Title [Estimation time in hrs] | Description | Time Taken (hrs) | Completion Date | Members | Labels | Card # | Card URL
Done | Suicide Bugs [5] | These are brightly colored cockroaches, that target the player and then ram into doing 3 dmg to the player and killing themselves. They have no armor and can be 1 shotted. | 5 | 2015-12-14 | DF | M4 Requirement | 76 | https://trello.com/c/X34QcFcm
Done | Presentation Material | https://docs.google.com/presentation/d/1x-sa04UnyZaRe21tLOZGJywoaSiP7VPB9HG24QmP8vw/edit?usp=sharing | 1 | 2015-12-14 | DV,DF | M4 Requirement | 74 | https://trello.com/c/5WVeYnK1
Done | Player Also has HP [2] |  | 2 | 2015-12-14 | DF | M4 Requirement | 45 | https://trello.com/c/ZgFRz7wX
Done | Fix Sounds [1] |  | 1 | 2015-12-14 | DF,NN | M4 Requirement | 54 | https://trello.com/c/3ZQ9EqyH
Done | Implement wave [13] |  | 13 | 2015-12-14 | NN | M4 Requirement | 43 | https://trello.com/c/oPy0ko7X
Done | UI : Wave Count [1] |  | 1 | 2015-12-14 | NN | M4 Requirement | 21 | https://trello.com/c/KaKBoFHF
Done | NPC and Player Stats [1] | NPCs will have 30-75hp, and attack1 does 25dmg, attack2 does 10dmg. These stats will track current hp. Attack2 also slows down it's target for 10 seconds. | 2 | 2015-12-14 | DV,DF | M4 Requirement | 36 | https://trello.com/c/wbCplRwA
Done | Submittibles [0.5] |  | 0.5 | 2015-12-14 |  | M4 Requirement | 75 | https://trello.com/c/8UQrueHp
Done | Nest Module: has legit model [2] |  | 2 | 2015-12-08 | GH | M4 Requirement | 70 | https://trello.com/c/MBLwuLIl
Done | Queen Module: has legit model [2] |  | 2 | 2015-12-08 | GH | M4 Requirement | 69 | https://trello.com/c/tchFzvzA
Done | Nest Module: is kill-able with hitpoints [0.5] |  | 0.5 | 2015-12-08 | DV | M4 Requirement | 73 | https://trello.com/c/Wd47vftb
Done | Queen Module: Flies in Path [1] |  | 1 | 2015-12-08 | DV | M4 Requirement | 66 | https://trello.com/c/gGkaBfes
Done | Queen Module: spawns enemies [1] |  | 1 | 2015-12-08 | DV | M4 Requirement | 67 | https://trello.com/c/JJUGa4BH
Done | Nest Module: spawns enemies [0.5] |  | 0.5 | 2015-12-08 | DV | M4 Requirement | 72 | https://trello.com/c/qfIMLz09
Done | Queen Module: is kill-able with hitpoints [2] |  | 2 | 2015-12-08 | DV | M4 Requirement | 68 | https://trello.com/c/ZDM1r2Dx
Done | Nest Module [5] | 3 types of units initially: -Workers (these focus on building new nests or repairing the current ones) -Warriors (focus on attacking the player) -Drones (focus on attacking the mouth) Game starts with initial nest which spawns ants. Randomly spawns unit types, but has a 25% of spawning warriors and workers. Has a 50% chance of spawning drones. Actual spawn ratios may be off due to random chance. Workers head to the closest nest with less than full health. (Nests have 10 hp). Unbuilt nests count as having 0 hp, but do not have spawning capabilities turned on. Level starts with one pre-built nest, but has invisible nests that can be build by workers. Each worker increases nest hp by +1 every 3 seconds when touching the nest node. If all nests are full hp, they act like drones and head towards the mouth. Warriors locate the player and head towards his location and attempt to kill the player by attacking them. This AI will be the most complicated and not finished until Milestone 4. Needs more discussion. Drones are simple and as soon as the spawn head straight for the mouth ignoring the player (may change? maybe attack the player if they get close enough to player or are attacked by player?) | 5 | 2015-12-08 |  | M4 Requirement | 55 | https://trello.com/c/7UCG0HS5
Done | Print Questionaires |  |  | 2015-11-12 12:00 | DF | M3 Requirement | 52 | https://trello.com/c/yClEbIYX
Done | make backlog from trello [1] |  | 1 | 2015-11-12 12:00 | DV | M3 Requirement | 62 | https://trello.com/c/2b3EA1r3
Done | Group Submittables [3] |  | 3 | 2015-11-12 12:00 | DF,DV,GH,NN | M3 Requirement | 56 | https://trello.com/c/F5tacsp6
Done | Fix Sounds [1] |  | 1 | 2015-11-12 12:00 | DF,NN | M3 Requirement | 54 | https://trello.com/c/3ZQ9EqyH
Done | Add instructions to the start screen. [3] |  | 3 | 2015-11-12 12:00 | NN | M3 Requirement | 49 | https://trello.com/c/kFRhq7Re
Done | Questionnaire Form |  |  | 2015-11-12 12:00 | DF,DV | M3 Requirement | 51 | https://trello.com/c/xrIRaj4s
Done | Materials/Textures for room [3] |  | 3 | 2015-11-12 12:00 | DV,GH | M3 Requirement | 61 | https://trello.com/c/q8WAxPSZ
Done | research thirdperson view [2] |  | 2 | 2015-11-12 12:00 | DV | M3 Requirement | 60 | https://trello.com/c/PfHMBtDz
Done | survey summary [1] |  | 1 | 2015-11-12 12:00 | DV | M3 Requirement | 57 | https://trello.com/c/VUiyIcVh
Done | Individual Milestone 3 Requirements |  |  | 2015-11-10 12:00 | DF,DV,GH,NN | M3 Requirement | 53 | https://trello.com/c/3crrtEKS
Done | Bedroom Level Basic Detail: for M4 [5] | Include from this: https://www.assetstore.unity3d.com/en/#!/content/8329 | 5 | 2015-11-10 12:00 | GH,NN,DV | M3 Requirement | 65 | https://trello.com/c/eKaPoMEx
Done | Fix clipping [2] |  | 2 | 2015-11-10 12:00 | DV,DF | M3 Requirement | 63 | https://trello.com/c/XZTPq5PI
Done | pause menu [2] |  | 2 | 2015-11-10 12:00 | NN | M3 Requirement | 50 | https://trello.com/c/ckEY5RZP
Done | survey (blank) pdf [0] |  | 0 | 2015-11-10 12:00 | DV | M3 Requirement | 59 | https://trello.com/c/g1PJjJNz
Done | survey excel (responses) [0.5] |  | 0.5 | 2015-11-10 12:00 | DV | M3 Requirement | 58 | https://trello.com/c/fO6H11zB
Done | Individual Progress Reports | Each member of the group should turn in a separate progress report. Submit a plain text/html file including: * A rating of each of the other members of your group. * how much they contributed to the project * how well they communicated with the group. * The rating should be on a scale of 1 to 5, with 5 being the best. You can also include comments. |  | 2015-10-15 16:00 |  | M2 Requirement | 6 | https://trello.com/c/FpWgZWYy
Done | Game design document [3] | Write a game design document that describes the design and implementation of your group's game * Start from Pitch * include information about the software design * implementation of the game, Collab Doc Here: https://docs.google.com/document/d/1vkhe1z7SB_qGJzgdHhzdKpMxdQyyBWziZdrJczPwTfs | 3 | 2015-10-15 16:00 | DF,GH,DV,NN | M2 Requirement | 2 | https://trello.com/c/EjCdEH7u
Done | Use of Backlog | As group members complete implementation of user stories in the backlog, add information to your group's backlog.xls (trello, we will export this information to excel) Each Story should have: * Completion date * Assignee * Time logged |  | 2015-10-15 16:00 | DV,DF,GH,NN | M2 Requirement | 3 | https://trello.com/c/UWEzv6Ps
Done | Spawner and Level Re-Do [5] | Greg's spawner gets implemented with a slightly bigger/better level design. Suggest adding the bed from this page: https://www.assetstore.unity3d.com/en/#!/content/8329 (free unity asset store) | 5 | 2015-10-15 16:00 | GH,DF | M2 Requirement | 35 | https://trello.com/c/ZO3YxZdI
Done | Research scene collaboration [0.5] |  | 0.5 | 2015-10-15 16:00 | NN | M3 Requirement | 34 | https://trello.com/c/2U8BVSlY
Done | Beginning UI (Start Game) |  | 1.5 | 2015-10-14 12:00 | NN |  | 24 | https://trello.com/c/3HR9V7Vf
Done | UI : Spit Ammo HUD |  | 1.5 | 2015-10-14 12:00 | NN |  | 33 | https://trello.com/c/bQXJI8BG
Done | Repository Information [0.5] | Update Readme.txt to include: * Where the GitHub repository is located * How the professor can access it | 0.5 | 2015-10-14 12:00 | DV | M2 Requirement | 5 | https://trello.com/c/zujDAx9j
Done | Game is Playable [5] | Game should include all of the most important features in the game, even if they are somewhat simplified. The idea is to get other people to play your game and give you feedback. If your game doesn't give players a good feel for what the game is about, they probably won't be able to provide useful feedback. | 8 | 2015-10-14 12:00 | DV,DF,GH,NN | M2 Requirement | 1 | https://trello.com/c/LGfNo3Qh
Done | Add variable "R" to restart game modifiable [0.5] |  | 0.5 | 2015-10-13 12:00 | NN,DV,DF |  | 38 | https://trello.com/c/GyxhOARL
Done | Game over UI [1] |  | 1 | 2015-10-13 12:00 | NN,DV |  | 26 | https://trello.com/c/Ty97U7zN
Done | Enemy Basic AI [5] | Enemies will spawn and then ignore the player entirely and then make a straight bee-line toward the mouth/center of level. | 5 | 2015-10-13 12:00 | NN,GH | M2 Requirement | 13 | https://trello.com/c/tW1G6IuY
Done | UI : Timer [0.5] |  | 0.5 | 2015-10-13 12:00 | NN |  | 18 | https://trello.com/c/hs8bjeXT
Done | UI : Health [0.5] |  | 0.5 | 2015-10-13 12:00 | NN |  | 19 | https://trello.com/c/bPVwwY9X
Done | Character Attack 1 (bite) [3] | Attack1 implementation: triggers a bite animation from player object and uses a collision box that extends slightly from the spiders mouth. If an enemy is touching or in that box, when mouse1 is pressed, that enemy will take hp damage. | 3 | 2015-10-13 12:00 | DF | M2 Requirement | 31 | https://trello.com/c/jbCLyCqw
Done | Character Movement [0.5] |  | 0.5 | 2015-10-13 12:00 | DF | M2 Requirement | 9 | https://trello.com/c/sS6FA3Qu
Done | Level Model [1] |  | 1 | 2015-10-13 12:00 | GH | M3 Requirement | 22 | https://trello.com/c/d57loNfv
Done | Game over Logic [1] |  | 1 | 2015-10-13 12:00 | NN,DV,DF | M3 Requirement | 27 | https://trello.com/c/hayfcbT6
Done | Character Attack 2 (spit) [3] | Attack2 implementation: fires a single projectile in a parabolic arc. If the projectile object hits an enemy object’s hitbox, it does a small amount of hp damage, and apply a slow effect that will slow that enemies movement rate for 10 seconds. Player can aim mouse higher to increase the arc of the fired projectile, etc. Player starts with three shots, and needs to wait 25 seconds (subject to change), before a shot will ‘recharge’ and be able to be shot again. | 3 | 2015-10-12 12:00 | NN,DV | M2 Requirement | 12 | https://trello.com/c/ackeaFUj
Done | Get Basic game from M1 to Repo [2] |  | 1 | 2015-10-02 12:00 | DV |  | 30 | https://trello.com/c/YKi42Jzw
Done | Submittables / Grading [1] |  | 1 |  |  | M2 Requirement | 8 | https://trello.com/c/6ocZmdmE
Done | Plan for Milestone 3 [0.5] | * Explain which user stories you will be implementing for Milestone 3 * Explain how they relate to the feedback you receive and the game design concepts we talk about in class. | 0.5 |  | DV,DF,GH | M2 Requirement | 4 | https://trello.com/c/2r5Jegu6
Done | Update ReadMe [0.5] | README.html or README.txt file that includes the following sections: * how to play your game, * your group's plan for Milestone 3, * repository information. | 0.5 |  | DV,DF | M2 Requirement | 7 | https://trello.com/c/9TS0ggTC

## Archived Epic Stories
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL